## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Collect historical visa data | Must | None | Individual | Completed
Sprint 1 | Sprint 1 | US-02 | Data cleaning and preprocessing | Must | US-01 | Individual | Completed
Sprint 2 | Sprint 2 | US-03 | EDA and visualization | Should | US-02 | Individual | Completed
Sprint 2 | Sprint 2 | US-04 | Feature engineering | Should | US-03 | Individual | Completed
Sprint 3 | Sprint 3 | US-05 | Train regression models | Must | US-04 | Individual | Completed
Sprint 3 | Sprint 3 | US-06 | Model evaluation & tuning | Must | US-05 | Individual | Completed
Sprint 4 | Sprint 4 | US-07 | Build web application | Should | US-06 | Individual | Completed
Sprint 4 | Sprint 4 | US-08 | Deploy application | Should | US-07 | Individual | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US001 | T1 | Collect visa application dataset and verify structure | 2025-12-04 | 2025-12-08 | Individual | Data Collection | Done | 6 | bar: Day 1 to Day 2
US001 | T2 | Clean missing values and normalize visa features | 2025-12-09 | 2025-12-09 | Individual | Data Cleaning | Done | 10 | bar: Day 2 to Day 4
US002 | T3 | Train ML model (Random Forest) for visa status prediction | 2025-12-13 | 2025-12-10 | Individual | Model Training | Done | 12 | bar: Day 3 to Day 6
US003 | T4 | Evaluate and tune ML model for better accuracy | 2025-12-19 | 2025-12-11 | Individual | Model Evaluation | Done | 8 | bar: Day 4 to Day 6
US004 | T5 | Create frontend dashboard for visa prediction results | 2025-12-26 | 2026-01-06 | Individual | UI Development | Done | 10 | bar: Day 5 to Day 8
US004 | T6 | Deploy backend and frontend to test environment | 2026-01-07 | 2026-01-22 | Individual | Deployment | Done | 8 | bar: Day 6 to Day 9
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | None | Work initiated
Sprint 1 | Day 2 | Missing data | Synthetic data used
Sprint 2 | Day 1 | Plot delay | Schedule adjusted
Sprint 3 | Day 1 | ML model training taking longer due to high feature dimensionality | Model tuned
Sprint 4 | Day 1 | Deployment issue | Config fixed
Sprint 4 | Day 1 | Frontend unable to fetch prediction results due to CORS policy | Enabled CORS in Flask backend and tested API connectivity

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 28/11/2025 | 2025-11-12 | Individual | Document visa data preprocessing steps clearly | Training model without validating raw data | Collaborating during data cleaning | Created shared preprocessing and data dictionary document
2 | Sprint 2 | 2025-12-12 | 25/12/2025 | Individual | Use version control for datasets and model files | Using full dataset without sampling | Validating EDA insights before feature engineering | Implemented dataset & model versioning
3 | Sprint 3 | 26/12/2025 | 2026-08-01 | Individual | Write clear feature definitions and model assumptions | Random hyperparameter tuning | Evaluating models using MAE & RMSE consistently | Finalized optimized Random Forest model
4 | Sprint 4 | 2025-09-26 | 22/01/2026 | Individual | Perform integration testing in parallel | Waiting until final sprint for testing | Regular cross-team sync meetings | Scheduled weekly integration & demo sessions