## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
|  |  | Missing values error | Handled null values | Individual | Closed | Resolved | 06-Dec-2025 | closed | Dataset validated successfully
|  |  | Visualization scale issue | Adjusted plots | Individual | Closed | Resolved | 16-Dec-2025 | closed | Seasonal patterns identified
|  |  | Model overfitting | Hyperparameter tuning | Individual | Closed | Resolved | 29-Dec-2025 | closed | MAE and RMSE improved
|  |  | API timeout | Optimized backend | Individual | Closed | Resolved | 03-Jan-2026 | closed | Output displayed correctly
|  |  | Date parsing error | Fixed date format | Individual | Closed | Resolved | 06-Jan-2026 | closed | Target variable generated correctly
|  |  | UI validation missing | Added validation | Individual | Closed | Resolved | 11-Jan-2026 | closed | User-friendly form
|  |  | Deployment config error | Updated environment | Individual | Closed | Resolved | 16-Jan-2026 | closed | Application deployed successfully

## Sheet2
Logical
User Interface
Maintainability
Standards
Others